## Backlog
Item nr | Sprint | MoSCoW | Widget | Description | Finished
1 | 1 | M | ProcessInsight | Draft widget with 6 processsteps heatmap | Y
2 | 1 | M | DepartmentInsight | Draft with total number of examinations, Average per FTE, Number per ExaminationType and Employee | Y
3 | 1 | M | WaitingroomInsight | Draft with time, seats, speedometer with minutes delay | Y
4 | 1 | S | All | Test connection via JSON | Y
5 | 1 | C | DepartmentInsight | Filtering per ExaminationType and Employee | Y
6 | 2 | M | ProcessInsight | Different visualisation with icons | Y
7 | 2 | M | DepartmentInsight | Different icon for Hospital
8 | 2 | M | All | Connection via JSONP | Y
9 | 2 | S | All | Remote connection database | Y
10 | 2 | C | All | Dragable widgets | Y
11 | 2 | S | All | Properties widgets | Y
12 | 2 | M | DepartmentInsight | Simplify selection on donut | Y
13 | 2 | S | DepartmentInsight | Reset of donut in the middle of the donut | Y
14 | 2 | M | WaitingroomInsight | Fonts different, remove room patientnumber visualisation, Time in the center, Titles in center | Y
15 | 2 | S | ProcessInsight | Representative data for processing | Y
16 | 3 | M | All | Widgets on separate tabs | N
20 | 3 | M | ProcessInsight | Put steps in one horizontal line next to each other | N
19 | 3 | M | ProcessInsight | Filter on examination group for all steps | N
21 | 3 | M | ProcessInsight | Change graph icons into speedometer with number in the middle (example in ProcessInsight sheet) | N
22 | 3 | M | ProcessInsight | Clicking on an process step should pop-up list with the underlaying data (simple table grid) | N
25 | 3 | M | DepartmentInsight | Select detail level/range (year, month, week, day, part of the day to forecast workload) | N
27 | 3 | M | WaitingroomInsight | No speedometers aymore, only ON TIME or delay in minutes (+xx minutes) no negative values | N
17 | 3 | S | All | Enable/Disable widgets | N
26 | 3 | S | WaitingroomInsight | Add news ticker below or full news articles Right of the clock (http://www.nu.nl/rss/Gezondheid) | N
23 | 3 | S | ProcessInsight | Clicking on an process step should zoom-in showing the different Examination Group Types with Inidividual speedometers | N
24 | 3 | S | ProcessInsight | Alternative version of the widget with a picto-flow understandable for patients | N
28 | 3 | S | ProcessInsight | Make different visualisations in different widgets to be able to switch and discuss the best visualization with the client, this will also test the dragging and enabling of widgets in a dashboard | N
29 | 3 | C | All | Enable users to define targets on client side input/settings | N
30 | 3 | C | All | Make some simple style components set by user (logo, colors, …) | N
18 | 3 | C | All | Dummy widgets with nothing to show selection with dragable widgets which can be turned on or off | N

## Sprintlog 1 (hidden)
Item nr | Sprint | MoSCoW | Widget | Description | Finished
1 | 1 | M | ProcessInsight | Draft widget with 6 processsteps heatmap | Y
2 | 1 | M | DepartmentInsight | Draft with total number of examinations, Average per FTE, Number per ExaminationType and Employee | Y
3 | 1 | M | WaitingroomInsight | Draft with time, seats, speedometer with minutes delay | Y
4 | 1 | S | All | Test connection via JSON | Y
5 | 1 | C | DepartmentInsight | Filtering per ExaminationType and Employee | Y

## Sprintlog 2 (hidden)
Item nr | Sprint | MoSCoW | Widget | Description | Finished
6 | 2 | M | ProcessInsight | Different visualisation with icons | Y
7 | 2 | M | DepartmentInsight | Different icon for Hospital
8 | 2 | M | All | Connection via JSONP | Y
9 | 2 | S | All | Remote connection database | Y
10 | 2 | C | All | Dragable widgets | Y
11 | 2 | S | All | Properties widgets | Y
12 | 2 | M | DepartmentInsight | Simplify selection on donut | Y
13 | 2 | S | DepartmentInsight | Reset of donut in the middle of the donut | Y
14 | 2 | M | WaitingroomInsight | Fonts different, remove room patientnumber visualisation, Time in the center, Titles in center | Y
15 | 2 | S | ProcessInsight | Representative data for processing | Y

## Sprintlog 3 (hidden)
Item nr | Sprint | MoSCoW | Widget | Description | Finished
16 | 3 | M | All | Widgets on separate tabs | N
17 | 3 | M | All | Enable/Disable widgets | N
18 | 3 | C | All | Dummy widgets with nothing to show selection with dragable widgets which can be turned on or off | N
19 | 3 | M | ProcessInsight | Filter on examination group for all steps | N
20 | 3 | M | ProcessInsight | Put steps in one horizontal line next to each other | N
21 | 3 | M | ProcessInsight | Change graph icons into speedometer with number in the middle (example in ProcessInsight sheet) | N
22 | 3 | M | ProcessInsight | Clicking on an process step should pop-up list with the underlaying data (simple table grid) | N
23 | 3 | S | ProcessInsight | Clicking on an process step should zoom-in showing the different Examination Group Types with Inidividual speedometers | N
24 | 3 | S | ProcessInsight | Alternative version of the widget with a picto-flow understandable for patients | N
25 | 3 | M | DepartmentInsight | Select detail level/range (year, month, week, day, part of the day to forecast workload) | N
26 | 3 | S | WaitingroomInsight | Add news ticker below or full news articles Right of the clock (http://www.nu.nl/rss/Gezondheid) | N
27 | 3 | M | WaitingroomInsight | No speedometers aymore, only ON TIME or delay in minutes (+xx minutes) no negative values | N
28 | 3 | S | ProcessInsight | Make different visualisations in different widgets to be able to switch and discuss the best visualization with the client, this will also test the dragging and enabling of widgets in a dashboard | N

## ProcessInsight
2
DAYS
2
DAYS
2
DAYS
2
DAYS
2
DAYS
2
DAYS
2
DAYS
5
0
6
DAYS
4
2
3
DAYS
4
1
2
DAYS
5
0
3
DAYS
5
0
2
DAYS
5
0